## Slide 1
NESC Review Board
Assessment Plan Update
Flight Mechanics Analysis Tools Interoperability and Component Sharing TI-18-01313
Daniel G. Murri
October 17, 2019

## Slide 2: Outline
Acronyms
Background
Scope
Key Stakeholders
Team List
Special Requirements
Technical Activities
Plan Update
Deliverables
Disengagement Criteria
Resources

## Slide 3: Acronyms
SoS System of Systems
GMAT General Mission Analysis Tool
MONTE Mission-Analysis Operations Navigation Toolkit Environment
NESC NASA Engineering and Safety Center
ODTBX Orbit Determination Toolbox
POST Program to Optimize Simulated Trajectories
SEP Solar Electric Propulsion
API Application Programming Interface
O-REx OSIRIS-REx Mission

## Slide 4: Background: GMAT, Monte, Copernicus
Legacy, Enterprise Systems
Customers
  Together support 30+ flight projects and development efforts
Mission Lifecycle:
  Design
  Analysis
  Ops
Applications
  Orbit Determination
  Error Analysis
  Trajectory Optimization
  Flight Products
  Development
  Many others
Monte: Landing Site Statistical Hazard Avoidance
GMAT: Lunar Ice Cube EM1 Launch,
through Lunar Flyby, to Lunar
Capture using SEP
Copernicus: NRHO to DRO Transfer in the Earth Moon System

## Slide 5: Scope
Focus on Three Key Areas
    Enterprise SoS Integration: Develop and mature API and system interfaces to allow enterprise applications to share information and/or capability with each other and with other programming environments.
    Component Sharing: Complete integration of OpenFrames graphics component originally developed for Copernicus into GMAT and deprecate GMAT’s legacy graphics component.
    Lessons Learned: Develop technical and legal lessons learned for integration of NASA’s flight mechanics systems.
      Interface standards/protocols
      Legal/policy lessons to enable sharing of source and binaries among centers/projects
Strategy
    Focus SoS integration on use cases that tools cannot currently support.
    Focus on low hanging fruit to eliminate duplicative graphics components between GMAT and Copernicus.

## Slide 6: Key Stakeholders
Flight mechanics analysts and engineers
Chief engineers and project managers for existing and future programs, projects, and/or tasks that involve mission analysis, navigation, trajectory optimization, and mission operations to any destination
Key individual stakeholders:
  John Lynch, Director of the Flight Dynamics Facility at NASA Goddard Space Flight Center (GSFC)
  Rich Burns, Director Space Science Missions Operations (SSMO) at NASA GSFC
  Melissa McGuire, Deep Space Gateway (DSG) trajectory design lead at NASA Glenn Research Center
  O-REx Analysts
  Europa Clipper Analysts

## Slide 7: Team List
Name | Discipline | Organization | Contact Number | Email
Core Team |  |  |  | 
Daniel Murri | NESC Lead | LaRC | 757-864-1160 | daniel.g.murri@nasa.gov
Steven Hughes | Technical Lead, GMAT Lead | GSFC | 301-281-0145 | steven.p.hughes@nasa.gov
Gerald Condon | Copernicus Lead | JSC | 281-483-8173 | gerald.l.condon@nasa.gov
Roby Wilson | Monte-Copernicus Task Lead | JPL | 818.393.5301 | roby.s.wilson@jpl.nasa.gov
Ricardo Restrepo | Monte-Copernicus Analyst | JPL | 818-354-1951 | ricardo.l.restrepo@jpl.nasa.gov
Ted Drain | Monte Lead Programmer | JPL | 818-354-1149 | theodore.r.drain@jpl.nasa.gov
Scott Evans | Monte Task Manager | JPL | 818-393-6462 | scott.e.evans@jpl.nasa.gov
Anubhav Kamath | Copernicus Developer | JSC/Jacobs Technology | 301-286-4026 | anubhav.h.kamath@nasa.gov
Jacob Williams | Copernicus Developer | JSC/Jacobs Technology | 281-461-5921 | jacob.williams-1@nasa.gov
Noble Hatten | GMAT Analyst | GSFC | 301.286.4026 | noble.hatten@nasa.gov
Ravishankar Mathur | GMAT Developer | GSFC/Emergent Space Technologies, Inc. | 301-345-1535 | ravishankar.mathur@nasa.gov
Darrel Conway | GMAT Developer | GSFC/Thinking Systems Inc. | 623-298-4530 | djc@thinksysinc.com
John McGreevy | GMAT Developer | GSFC/Emergent Space Technologies, Inc. | 301-345-1535 | john.mcgreevy@emergentspace.com

## Slide 8: Team List, cont.
Name | Discipline | Organization | Contact Number | Email
Consultants |  |  |  | 
Michael Aguilar | NASA Technical Fellow for Software | LaRC | 757-864-2810 | michael.l.aguilar@nasa.gov
Steve Slojkowski | FDF Analyst | GSFC | 301-286-1957 | steven.e.slojkowski@nasa.gov
Joel Parker | ODTBX Lead | GSFC | 301-286-3604 | joel.j.k.parker@nasa.gov
Business Management |  |  |  | 
Linda Moore | Program Analyst | LaRC/MTSO | 757-864-9293 | linda.j.moore@nasa.gov
Assessment Support |  |  |  | 
Missy J. Strickland | Project Coordinator | LaRC/AMA | 757-864-2528 | melissa.j.strickland@nasa.gov
Linda I. Burgess | Planning and Control Analyst | LaRC/AMA | 757-864-9139 | linda.i.burgess@nasa.gov
Leanna S. Bullock | Technical Editor | LaRC/AMA | 757-864-2512 | leanna.s.bullock@nasa.gov

## Slide 9: Technical Activities: Executive Summary of Status
Task | Name/Description | Status
Task 1 | GMAT API Interface/ Monte Interfaces | On track, only behind schedule by the duration of the furlough.
Task 2 | OpenFramesInterface Integration in GMAT | Late due to furlough and long lead time in getting contract in place. There is no significant impact, and this task will be completed November 2019, well before the completion of the overall effort.
Task 3 | Monte-Copernicus Interfaces | Significantly behind schedule; we will discuss updated plan in later slides.
Task 4 | Lessons Learned | Largely dependent on Tasks 1 and 3. Will be completed on schedule at the end of the assessment.

## Slide 10: Task 1 GMAT API: Summary
Task Overview: Implement an API for GMAT
Goals:
  Make GMAT components available to Python, MATLAB, and JAVA
  Interface GMAT with other NASA tools through the API developed in this assessment
Completed Deliverables
  Design complete: 3/30/2019 (planned: 12/31/2018)
  Alpha releases: May and August 2019
  Use case 1 (Beta release)
    Goal: Access to force models, propagation, measurements, scripting
    Packaging complete: October 2019 (planned: September 2019)
  Furlough delayed the design review by 3 months; now caught up
Future Deliverables:
  Use case 2 (production release)
    Goal: Interoperability with MONTE and ODTBX
  Final assessment

## Slide 11: Task 1 GMAT API Accomplishments
Exposed highest priority system interfaces
Strategic enhancements
  System-level help
  Simplified attribute access
  Code updates for found issues
User documentation
Current application at GSFC
  Measurement modeling for the FDF*
  Dynamics modeling for LISA optimization
  Planning for JAT replacement in ODTBX
“This application of the API is something we’ve been trying to do in the FDF for years. Thanks to the API, it’s now easy for us to compute real-time residuals versus live incoming tracking data.”
—S. Slojkowski, GSFC

## Slide 12: Task 2 OpenFramesInterface: Summary
Task Overview: Test, debug, and document the OpenFramesInterface plugin for GMAT
Goal: Eliminate duplication of graphics components in GMAT and Copernicus and use a single graphics engine in both tools.
High-level deliverable status:
Deliverable | Planned Date | Actual Date
Create test plan document | June 2019 | July 2019
Develop system & regression tests | Sep 2019 | Oct 2019
End-user documentation | Nov 2019 | In Progress
Critical bug fixes | Oct 2019 | Oct 2019
Note: Furlough and contract initiation delayed start, but this task is no longer at risk and will finish in November.

## Slide 13: Task 2 OpenFramesInterface: Accomplishments
Testing – Incorporated tests into GMAT GUI test system
  Verification: Created 12 system tests against OFI use cases
  Validation: Created >20 functional tests (e.g., range checks)
Bug fixes
  Fixed several usability issues uncovered during formal testing
  Started fixing GMAT-console startup crash on Linux
OFI integration into GMAT
  Released OFI with GMAT R2019a Beta (May 2019)
  Added OFI to GMAT nightly build
Documentation
  Contains build documentation (for developers) and end-user documentation
  GMAT contains stub pointers to OFI Wiki-based docs

## Slide 14: Task 2 OpenFramesInterface: Impact
Graphics capability funded by multiple projects is already shared between tools!
Sensor Cones: CATALYST
Shadows: COPERNICUS
High Fidelity Terrain

## Slide 15: Task 3 Monte-Copernicus Integration: Summary
Task Overview: Implement an interface between Monte and Copernicus.
Goal: Improve interoperability between the JPL Monte and JSC Copernicus software sets to perform analysis that incorporates error analysis in the trajectory optimization process.
Issue: Integration of MONTE and Copernicus is significantly behind schedule due to furlough; increased demands of Gateway; and return to the Moon, EM1, Europa Clipper, Mars Insight, and Mars 2020.
Updated plan: Presented in the next slides.

## Slide 16: Updated Plan Executive Summary
Task 1: O-REx is using MONTE in backup mode for orbit determination and has GMAT setups for alternative maneuver planning options. We will start from those configurations and focus efforts on a flight project that is already using these tools in backup mode with the goal of demonstrating readiness for future projects at the completion of this effort.
Task 2: On track to be completed November 30, 2019. No planning update needed.
Task 3: Continue with progress on integration of Copernicus* and MONTE, but with decreased scope from the original plan, focusing efforts on Europa Clipper applications.
Task 4: On track to be completed at the end of assessment. No planning update needed.
  *Note: While JSC contribution is de-scoped, Copernicus-MONTE integration is enabled via previous investments made to Copernicus by the NESC.
Core Strategy: Focus the second half of the assessment on the integration of MONTE and GMAT using OD and maneuver planning/optimization for O-REx as the driving use case. Monte-Copernicus work will focus on Europa Clipper.

## Slide 17: Updated Plan: Key New Subtasks
Subtask | Subtask Name | Participants | Summary
Task 1.2 | Data Integration between Monte-GMAT | GMAT Developers Monte Developers | Share key data between systems, including ephemerides, covariance, and maneuver solutions, among others.
Task 1.3 | Component Integration between Monte-GMAT | GMAT Developers Monte Developers | Integrate core components (dynamics models/propagation) between systems requiring interfaces at the C++ level (previous plan would use Python interfaces between systems).
Task 3.1 | Integration of Monte-Copernicus | Monte Developer/ Analyst Copernicus Analyst/Developer | Share solutions between Monte and Copernicus to allow trajectories in computed in Monte to be visualized in Copernicus.

## Slide 18: GMAT API Updated Subtask Details
Phase 1: Subtask 1.2 Data Interoperability
  O-REx use case definition
  MONTE setup and GSFC training
  Ephemeris sharing
  Maneuver plan sharing
  Re-targeting
Phase 2: Subtask 1.3 Component Integration
  C++ interface definition
  Dynamics interface coding
  GMAT Monte dynamics model integration
  O-REx demonstration configuration
  Demonstrate OD in Monte and Optimization in GMAT using shared dynamics
Note that subtask 1.3 is a tighter integration than originally planned as it will use C++ rather than Python APIs.

## Slide 19: Monte-Copernicus Integration Updated Task Details
MonteCop interface development (Phase I, 4 months)
  Use Copernicus 3D visualization environment to visualize Monte trajectories.
  Use Copernicus visual optimization tools to tweak/improve pre-optimized Monte trajectories.
MonteCop interface development (Phase II, 4 months)
  Implement continuous state function in Copernicus to use as a cost (or constraint) function via plugins, making use of Monte pre-existing complex state functions.
  Implement bi-directional integration with the Cosmic high-fidelity optimization program.

## Slide 20: Assumptions
GMAT developers will perform majority of integration between GMAT and Monte, but will work with Monte developers for training and guidance.
The product of this work will not be used in the operational tool chain for O-REx; it will be used in shadow mode only.
This effort will not affect the O-REx schedule of operations.
Code level integration of dynamics models will require calls through C++ interfaces (as opposed to Python interfaces) for performance reasons.

## Slide 21: Schedule
PoP changes by ~1 year due to late start on key tasks, and increased scope of targeting return phase of O-REx.

## Slide 22: Deliverables
Deliverable | Content | Recipient/Availability
Monte Plugin | Software Application/Executable, Documentation | Government/Contractors, Commercial Use, Academia
GMAT API | Software Application/Executable, Documentation, Source Code | Open Source
Open Frames Shared Library | Software Application/Executable, Documentation, Source Code | Open Source
Best Practices | Documentation/Lessons Learned | NASA Projects

## Slide 23
Disengagement Criteria
The assessment will be complete when:
All software development and documentation tasks have been completed and demonstrated.
The flight dynamics systems have been validated with all changes completed.
The NESC final report has been written, presented, and approved.
Agency stakeholder users have been briefed on the new capabilities.

## Slide 24
Plan Approval
Approved: |  |  |  | 
 | NESC Director |  | Date | 

## Slide 25
Revision History
(Updated Assessment Plan)
Version | Description of Revision | Office of Primary Responsibility | Effective Date
1.0 | Initial release | Daniel G. Murri, NASA Technical Fellow for Flight Mechanics, LaRC | 05/17/2018
2.0 | Updated plan focusing on O-REx and Europa Clipper | Daniel G. Murri, NASA Technical Fellow for Flight Mechanics, LaRC | Awaiting NRB approval

## Slide 26: Backup Slides

## Slide 27: Solution: SoS Integration
Start from prototype API/Integration efforts.
Develop version 1.0 of API interfaces and integration components allowing tools to make low-level system calls.
Demonstrate interoperability on key use case, integrated orbit determination, and path planning optimization.
Allow enterprise systems to:
  Communicate with each other to avoid duplication.
  Communicate with common programming environments to enable integration with new applications, such as ground test environments and simulators.
Programming Environments
GMAT Core
GMAT C++ API
SWIG API
Copernicus, OD Toolbox, Others
Monte Core
Python API

## Slide 28: Solution: Duplicate Component Elimination
Embrace existing graphics capability: OpenSceneGraph is an off-the-shelf, open source 3D graphics toolkit, used by application such as visual simulation, games, virtual reality, scientific visualization and modelling.
Extend the OpenFrames flight mechanics graphics API for trajectory visualization.
Complete integration of GMAT-plugin that employs OpenFrames.
Integrate new functionality into Copernicus.
Deprecate GMAT’s heritage 3D graphics component.
Copernicus
OpenSceneGraph: open source high performance 3D graphics library
OpenFrames: open source API for trajectory graphics originally developed for Copernicus
GMAT
Generic OpenSceneGraph Applications
OpenSceneGraph Applications in Copernicus and GMAT

## Slide 29: Special Requirements
There is no need for access to proprietary servers and/or databases and no need for non-disclosure agreements for non-NASA team members.
Software Usage Agreements (SUA) are already in place that allow sharing of Monte, GMAT, and Copernicus between the software development teams and users of these systems.
There are no special requirements for facilities or tools to perform this assessment.

## Slide 30: Constraints
Integration efforts will employ Python inter-tool for interfaces as Monte and Copernicus already interface with Python (and GMAT does now, too).
GMAT API testing will be performed by extending the existing MATLAB-based test system and will employ the MATLAB-Python interface and the MATLAB-JAVA interface.