## Sheet1
GMAT API Work Items
Year 2 |  | Replan for OREx Support
Estimates (Days)
|  |  | JJM | DJC | SPH | Accepted | SPH | Est. | Due Date | Notes | Questions.
GMAT-MONTE Data Exchange
| OREx Use Case Definition |  | 5 | 8 | 10 | 8 | 2 | 8
|  |  | 10 | 10 | 15 | 20 | 3 |  |  | 2 people, at two work weeks.
| JPL Support |  |  | 20 | 0 |  |  |  |  | Low level support from JPL | Can we get training in MONTE?
| MONTE GMAT Interface Definition |  |  | 10 | 15 | 12 | 3 |  |  | Informal documentation on interface elements
| Data Interface Layer Definition and Coding |  |  | 10 | 20 | 15 | 4 |  |  | Detailed design and coding infrastructure. One of the data exchanges is working with hard coded data.
| Test and Debug |  |  | 5 | 15 | 5 | 3 |  |  | Preliminary testing of data flow/unit testing.
| Ephemeris Sharing |  |  |  | 0 |  |  |  |  | Likely SPK
|  | GMAT → MONTE | 4 | 3 | 12.5 | 4 | 2.5
|  | MONTE → GMAT | 4 | 5 | 7.5 | 4 | 1.5
|  | Round Trip Demonstrable | 2 | 2 | 0 | 2 |  |  |  | Close loop over ephem transfers
| GMAT API Finalization |  |  |  |  | 25 |  |  |  | Finishing API elements in GMAT. This is the first produciton version of GMAT API.
| Maneuver Plan Sharing |  | 15 | 15 | 15 | 15 | 3 |  |  | JJM: Best path for this would probably be to write a GMAT script, load it in the API and run it, then have the API grab the maneuver data and write it to file that MONTE can read
|  | Rerender GMAT Maneuver MONTE |  |  |  | 10 |  |  |  | Assume N.H. does this on his detail.
| Covariance Sharing |  | 15 | 25 | 10 | 20 | 2 |  |  | JJM: Do we need to add covariance propagation support to GMAT first, or is STM propagation sufficient?
| OREx Demonstration |  | 5 | 8 | 7.5 | 7 | 1.5
| Agile high value feature |  | 10 | 15 | 20 | 15 | 4 |  |  | assume some new feature will be identified during the work.
| Critical bug fixes |  | 10 | 15 | 20 | 15 | 4
| Documentation and Delivery Packaging |  | 10 | 12 | 15 | 15 | 3 |  |  | Need to write docs and bring
| Milestone 1 |  |  |  | 182.5 | 192 | 36.5 |  | Summer 2020
0
GMAT-MONTE C++ Level (Force) Modeling |  |  |  | 163 | 0 |  |  |  |  | JJM: This isn’t really a GMAT API task, I see it more of adding a new ForceModel that just happens to call into MONTE
|  |  | JJM | DJC | SPH | Accepted | SPH
| OREx Use Case Refinement |  | 5 | 5 | 10 | 7 | 2
| C++ Interface Defintion |  |  |  | 0
|  | Core Component Updates | 10 | 12 | 15 | 12 | 3
|  | Identified New Element Coding | 15 | 15 | 20 | 18 | 4
|  | Test and Debug | 10 | 15 | 20 | 15 | 4
| JPL Support |  |  | 20 | 0 |  |  |  |  | Low Level Support from JPL
| Dynamics Interface Coding |  | 10 | 15 | 10 | 12 | 2
| Test and Debug |  | 5 | 12 | 15 | 15 | 3
| Dynamics Extensions for Thrust |  | 10 | 15 | 25 | 20 | 5
| Test and Debug |  | 5 | 10 | 10 | 10 | 2
| OREx Demonstration Configuration |  | 5 | 10 | 5 | 7 | 1
| Agile high value feature |  | 10 | 15 | 20 | 15 | 4 |  |  | assume some new feature will be identified during the work.
| Round Trip Test and Debug |  | 5 | 12 | 20 | 12 | 4
| GMAT API Finalization |  |  |  |  | 20 |  |  |  | Finishing API elements in GMAT. This is the first produciton version of GMAT API.
| Critical bug fixes |  | 10 | 15 | 10 | 12 | 2
| OREx Demonstration |  | 5 | 5 | 15 | 7 | 3
| Documentation and Delivery Packaging |  | 10 | 15 | 15 | 12 | 3
| Final Report |  | 5 | 5 | 10 | 7 | 2
| Best practices |  |  | 5 | 20 | 10 | 4 |  |  | Estimate Assumes we are building as we go. This is to finalize.
| ODTBX API Integration |  | 8 | 20 | 0 | 12 |  |  |  | Replace JAT interfaces with GMAT
| Milestone 2 |  |  |  | 0 | 223 |  |  | Summer 2021
[5 empty] | Total FTE | 1.766